## Project Overview
HAUTE & HAZARD - Project Management Tracker
"Walk the runway, claim the turf, survive the evolution."
Project Start Date: | 2026-01-09
Target Release: | TBD
Current Phase: | Balance Testing
PHASE SUMMARY
Phase | Status | Start | End | Duration (Weeks) | % Complete | Notes
1. Core Balance Fixes | In Progress | 2026-01-09 | 2026-01-23 | 2 | 80% | P0/P1 fixes COMPLETE
2. Orange/Green Tenets | Not Started | 2026-01-23 | 2026-02-20 | 4 | 0% | 30 new cards + 2 queens
3. Playtest Alpha | Not Started | 2026-02-20 | 2026-03-20 | 4 | 0% | Internal testing
4. Visual Design | Not Started | 2026-03-06 | 2026-04-17 | 6 | 0% | Card templates, mats, icons
5. Rules Refinement | Not Started | 2026-03-20 | 2026-04-03 | 2 | 0% | Quickstart + edge cases
6. Playtest Beta | Not Started | 2026-04-03 | 2026-05-01 | 4 | 0% | External testing
7. Expansion: Versailles | Not Started | 2026-05-01 | 2026-06-12 | 6 | 0% | Court Rank system
8. Expansion: Molly House | Not Started | 2026-06-12 | 2026-07-24 | 6 | 0% | Mask system
9. Expansion: Studio 54 | Not Started | 2026-07-24 | 2026-09-04 | 6 | 0% | Fame Track system
10. Production Prep | Not Started | 2026-09-04 | 2026-10-02 | 4 | 0% | Print files, rulebook

## Task List
HAUTE & HAZARD - Detailed Task List
ID | Task | Phase | Priority | Status | Owner | Start | Due | Dependencies | Notes
T001 | Fix Rat Tail Purse infinite loop | 1. Core Balance | P0 - Critical | Complete |  | 2026-01-09 | 2026-01-10 | - | v3.1: Added "once per turn" restriction
T002 | Buff Necropolis brand (+1★) | 1. Core Balance | P1 - High | Complete |  | 2026-01-10 | 2026-01-12 | T001 | v3.1: All 5 cards +1★ buff applied
T003 | Cap Feather Boa at +3 Defense | 1. Core Balance | P1 - High | Complete |  | 2026-01-10 | 2026-01-11 | T001 | v3.1: Capped at +3 Defense max
T004 | Update Card Manifest with fixes | 1. Core Balance | P1 - High | Complete |  | 2026-01-12 | 2026-01-14 | T002, T003 | v3.1: Card Manifest + Rulebook updated
T005 | Playtest balance fixes | 1. Core Balance | P1 - High | Not Started |  | 2026-01-14 | 2026-01-23 | T004 | 5+ games minimum
T010 | Design Fever Dream cards (5) | 2. Orange/Green | P2 - Medium | Not Started |  | 2026-01-23 | 2026-01-30 | T005 | Common Orange brand
T011 | Design Trickster cards (5) | 2. Orange/Green | P2 - Medium | Not Started |  | 2026-01-30 | 2026-02-06 | T010 | Uncommon Orange brand
T012 | Design Mirror Maze cards (3) | 2. Orange/Green | P2 - Medium | Not Started |  | 2026-02-06 | 2026-02-10 | T011 | Ultra Rare Orange brand
T013 | Design Mx. Mirage (Queen) | 2. Orange/Green | P2 - Medium | Not Started |  | 2026-02-10 | 2026-02-12 | T012 | Orange Queen
T014 | Design Greenhouse cards (5) | 2. Orange/Green | P2 - Medium | Not Started |  | 2026-01-23 | 2026-01-30 | T005 | Common Green brand
T015 | Design Hibernate cards (5) | 2. Orange/Green | P2 - Medium | Not Started |  | 2026-01-30 | 2026-02-06 | T014 | Uncommon Green brand
T016 | Design Ancient Grove cards (3) | 2. Orange/Green | P2 - Medium | Not Started |  | 2026-02-06 | 2026-02-10 | T015 | Ultra Rare Green brand
T017 | Design Terra Firma (Queen) | 2. Orange/Green | P2 - Medium | Not Started |  | 2026-02-10 | 2026-02-12 | T016 | Green Queen
T018 | Design Orange/Green Stages (4) | 2. Orange/Green | P2 - Medium | Not Started |  | 2026-02-12 | 2026-02-16 | T013, T017 | Fun House, Identity Crisis, etc.
T019 | Balance review: new tenets | 2. Orange/Green | P2 - Medium | Not Started |  | 2026-02-16 | 2026-02-20 | T018 | ER analysis on all new cards
T020 | Create proxy card set | 3. Playtest Alpha | P2 - Medium | Not Started |  | 2026-02-20 | 2026-02-24 | T019 | Print-and-play proxies
T021 | Recruit alpha testers (5-10) | 3. Playtest Alpha | P2 - Medium | Not Started |  | 2026-02-20 | 2026-02-27 | - | Friends, local game groups
T022 | Run alpha playtest sessions | 3. Playtest Alpha | P2 - Medium | Not Started |  | 2026-02-27 | 2026-03-13 | T020, T021 | 10+ sessions, log results
T023 | Analyze playtest feedback | 3. Playtest Alpha | P2 - Medium | Not Started |  | 2026-03-13 | 2026-03-20 | T022 | Identify issues, prioritize fixes
T030 | Define color palette (final) | 4. Visual Design | P2 - Medium | Not Started |  | 2026-03-06 | 2026-03-10 | - | CMYK values for print
T031 | Design card template (front) | 4. Visual Design | P2 - Medium | Not Started |  | 2026-03-10 | 2026-03-20 | T030 | All slot types
T032 | Design card template (back) | 4. Visual Design | P2 - Medium | Not Started |  | 2026-03-20 | 2026-03-24 | T031 | Symmetrical, no tells
T033 | Design player mat | 4. Visual Design | P2 - Medium | Not Started |  | 2026-03-24 | 2026-04-03 | T031 | 6 slots + resource tracks
T034 | Create icon set | 4. Visual Design | P2 - Medium | Not Started |  | 2026-04-03 | 2026-04-10 | T030 | Resources, keywords, actions
T035 | Commission/generate card art | 4. Visual Design | P2 - Medium | Not Started |  | 2026-03-20 | 2026-04-17 | T031 | 125+ unique illustrations
T040 | Write Quickstart Guide | 5. Rules Refinement | P2 - Medium | Not Started |  | 2026-03-20 | 2026-03-27 | T023 | 5-minute learn version
T041 | Clarify edge cases document | 5. Rules Refinement | P2 - Medium | Not Started |  | 2026-03-27 | 2026-04-01 | T040 | FAQ format
T042 | Create turn reference card | 5. Rules Refinement | P2 - Medium | Not Started |  | 2026-04-01 | 2026-04-03 | T041 | Single page summary
T050 | Recruit beta testers (20-50) | 6. Playtest Beta | P3 - Low | Not Started |  | 2026-04-03 | 2026-04-10 | - | Online communities, cons
T051 | Distribute beta kits | 6. Playtest Beta | P3 - Low | Not Started |  | 2026-04-10 | 2026-04-17 | T035, T050 | Print-and-play or TTS
T052 | Collect beta feedback | 6. Playtest Beta | P3 - Low | Not Started |  | 2026-04-17 | 2026-05-01 | T051 | Surveys, session logs
T060 | Design Versailles expansion | 7. Versailles | P3 - Low | Not Started |  | 2026-05-01 | 2026-05-29 | T052 | Court Rank system + cards
T061 | Playtest Versailles | 7. Versailles | P3 - Low | Not Started |  | 2026-05-29 | 2026-06-12 | T060 | Balance with base game
T070 | Design Molly House expansion | 8. Molly House | P3 - Low | Not Started |  | 2026-06-12 | 2026-07-10 | T061 | Mask system + cards
T071 | Playtest Molly House | 8. Molly House | P3 - Low | Not Started |  | 2026-07-10 | 2026-07-24 | T070 | Balance with base game
T080 | Design Studio 54 expansion | 9. Studio 54 | P3 - Low | Not Started |  | 2026-07-24 | 2026-08-21 | T071 | Fame Track system + cards
T081 | Playtest Studio 54 | 9. Studio 54 | P3 - Low | Not Started |  | 2026-08-21 | 2026-09-04 | T080 | Balance with base game
T090 | Finalize card manifest | 10. Production | P3 - Low | Not Started |  | 2026-09-04 | 2026-09-11 | T081 | All cards, all sets
T091 | Create print-ready files | 10. Production | P3 - Low | Not Started |  | 2026-09-11 | 2026-09-25 | T090 | 300dpi, CMYK, bleed
T092 | Write final rulebook | 10. Production | P3 - Low | Not Started |  | 2026-09-18 | 2026-10-02 | T090 | Full rules + glossary
T093 | Get print quotes | 10. Production | P3 - Low | Not Started |  | 2026-09-25 | 2026-10-02 | T091 | 3+ manufacturers

## Card Tracker
HAUTE & HAZARD - Card Production Tracker
Tenet | Brand | Rarity | Card Count | Design | Balance | Art | Template | Print Ready
💗 Pink | Sugar Rush | Common | 20 | Complete | Complete | Not Started | Not Started | Not Started
💗 Pink | Hyper-Glitch | Uncommon | 10 | Complete | Complete | Not Started | Not Started | Not Started
♠️ Blue | Necropolis | Common | 15 | Complete | Complete | Not Started | Not Started | Not Started
♠️ Blue | Slasher | Uncommon | 10 | Complete | Complete | Not Started | Not Started | Not Started
♠️ Blue | Void | Ultra Rare | 10 | Complete | Complete | Not Started | Not Started | Not Started
💎 Purple | Velvet Trap | Common | 20 | Complete | Complete | Not Started | Not Started | Not Started
💎 Purple | Gilded Cage | Ultra Rare | 10 | Complete | Complete | Not Started | Not Started | Not Started
⭐ Yellow | Trash Can | Common | 15 | Complete | Needs Fix | Not Started | Not Started | Not Started
⭐ Yellow | Big Top | Uncommon | 10 | Complete | Needs Fix | Not Started | Not Started | Not Started
⭐ Yellow | Swamp Witch | Ultra Rare | 8 | Complete | Complete | Not Started | Not Started | Not Started
🧡 Orange | Fever Dream | Common | 15 | Not Started | Not Started | Not Started | Not Started | Not Started
🧡 Orange | Trickster | Uncommon | 10 | Not Started | Not Started | Not Started | Not Started | Not Started
🧡 Orange | Mirror Maze | Ultra Rare | 6 | Not Started | Not Started | Not Started | Not Started | Not Started
🌿 Green | Greenhouse | Common | 15 | Not Started | Not Started | Not Started | Not Started | Not Started
🌿 Green | Hibernate | Uncommon | 10 | Not Started | Not Started | Not Started | Not Started | Not Started
🌿 Green | Ancient Grove | Ultra Rare | 6 | Not Started | Not Started | Not Started | Not Started | Not Started
⬛ Neutral | Vogue Cards | Mixed | 14 | Complete | Complete | Not Started | Not Started | Not Started
⬛ Neutral | Starter Deck | Basic | 60 | Complete | Complete | Not Started | Not Started | Not Started
🎭 Special | Queens | Unique | 13 | Complete | Complete | Not Started | Not Started | Not Started
🎭 Special | Stages | Unique | 16 | Complete | Complete | Not Started | Not Started | Not Started
🎭 Special | Exterminations | Penalty | 25 | Complete | Complete | Not Started | Not Started | Not Started
TOTAL CARDS:

## Playtest Log
HAUTE & HAZARD - Playtest Session Log
Instructions: Log each playtest session. Use this data to identify balance issues and track game feel.
Session # | Date | Players | Duration | Winner | Winning Queen | Final SP | Dominant Strategy | Issues Found | Fun Rating (1-10) | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Status Key
STATUS & PRIORITY KEY
Task Status
Not Started | Task has not begun
In Progress | Work is actively underway
In Review | Awaiting feedback or approval
Complete | Task is finished
Blocked | Cannot proceed due to dependency or issue
Priority Levels
P0 - Critical | Game-breaking bug or blocker. Fix immediately.
P1 - High | Important issue affecting core gameplay. Fix this sprint.
P2 - Medium | Standard development task. Schedule normally.
P3 - Low | Nice-to-have or future consideration.
Card Progress Status
Complete | Card/set is finalized
In Progress | Currently being worked on
Needs Fix | Balance issue identified, needs revision
Not Started | Work has not begun

## v3.1 Changelog
Date | Change Type | Card/System | Old Value | New Value | Reason
2026-01-10 | Balance Fix | Rat Tail Purse | Unlimited use | Once per turn | Prevented infinite loop combo
2026-01-10 | Balance Buff | Medusa Locks | +2★ | +3★ | Necropolis brand underperforming
2026-01-10 | Balance Buff | Funeral Shroud | +2★ | +3★ | Necropolis brand underperforming
2026-01-10 | Balance Buff | Combat Boots | +1★ | +2★ | Necropolis brand underperforming
2026-01-10 | Balance Buff | Pale Foundation | +1★ | +2★ | Necropolis brand underperforming
2026-01-10 | Balance Buff | Skull Choker | +2★ | +3★ | Necropolis brand underperforming
2026-01-10 | Balance Nerf | Feather Boa | Unlimited | Max +3 Defense | Purple Fortress too strong
2026-01-10 | Documentation | Card Manifest | v3.0 | v3.1 | Applied all balance changes
2026-01-10 | Documentation | Rulebook | v3.0 | v3.1 | Updated with new card text